## Slide 1: Claims Management – The Future
May 25, 2023

## Slide 2: Who are we?
Chris Briggs
  Retired from TxDOT after 30 years in the Dallas District
  Served as the District Environmental Quality Coordinator and the Scheduling Coordinator
  Reviewed Claims and Inefficiencies
  Currently working at Garver managing schedules and reviewing claims and impacts

## Slide 3: Who are we?
Jerry Trotter
BSE-CE from Arkansas State University
30 years with ARDOT
2.5 years with Garver
Licensed in AR and TX

## Slide 4: Claims Management
How do we handle?
Notes: How do we handle these? Managing construction claims is a crucial aspect of project success and dispute resolution. This process involves identifying and documenting potential issues that may give rise to a claim, evaluating claim's validity, and attempting to negotiate a reasonable settlement. If the parties cannot reach a settlement, they may resort to litigation, which is the formal process of taking the claim to court or arbitration. By following the best practices of contract administration, communication, documentation, and dispute resolution, you can minimize and manage construction claims effectively.

## Slide 5: Agenda Topics
What are claims?
How are they managed?
How can we do better in the future?

## Slide 6: What are claims?

## Slide 7: What are claims?

## Slide 8: What are claims?

## Slide 9: What are claims?
A construction claim is...
the assertion of a right, that requires either more time and/or payment by either party of the contract (often the contractor), for compensation of the losses brought on by the other party's failure to uphold their portion of the responsibilities as defined in the contract.
Notes: Impacts not the owner or contractor’s fault? 3 parts to a claim. Ownership, cost and time.

## Slide 10: What are claims?
Causes of Claims in Construction
Project delays
Contract or construction disputes
Unforeseen circumstances
Poor project management
Design/contract errors and omissions
Accidents
Notes: Impacts not the owner or contractor’s fault? Give examples?

## Slide 11: How are they managed?
Resolution
Proactive
Objective
Accurate
Transparent
Notes: While some claims cannot be avoided. Many claims can be resolved in a more efficient manner, or simply prevented with a proactive, objective, accurate, and transparent approach to a resolution.
A timely and accurate outcome is beneficial to all parties involved.

## Slide 12: How are they managed?
How can we make the process better?
Bid realistically
Do not let claims sit on the backburner
Keep detailed records
Implement continuous monitoring
Risk management? Get into future detail later.
Notes: Bid realistically: know the plans, know your capabilities, know the contract, know the site, know and accept your risk, and bid as accurately as you can to make the project go better.
Do not let claims set: this aids in accuracy as all of the data and facts are current and not lost or forgotten. It provides both parties adequate opportunity to evaluate data and reach an accurate conclusion. Provides more trust in the facts as they are current and not having to be research or trust memory.
Keep detailed records: this goes without saying. This provides trust in the accuracy of what is being evaluated and aids in expediting the process
Implement continuous monitoring: again this is to provide true, accurate, trusted, and timely information.

## Slide 13: How are they managed?
1. Contractor
2. Owner
Notes: In a construction claims management process, there are two parties. One is making the claim and the other is preventing against it.

## Slide 14: How are they managed?
Preplan - evaluation/study/research/contract review. Geotechnical, Products, Resources, Weather, Contract.
Track and document internal controls. Labor, Equipment, Materials, Time, Schedule.
Understand and follow contract requirements.
Early identification of constructability issues.
Communicate!

## Slide 15: How are they managed?
Prebid - evaluation/study/research. Geotechnical, Design, Products, Owner resource availability.
Track and document internal controls. Labor, Equipment, Materials, Time, Schedule.
Understand and follow contract requirements.
Early identification of constructability issues.
Communicate!

## Slide 16: How can we do better?
Don’t Delay
Accurate/Realistic Bids
Detailed Records

## Slide 17: How can we do better?
A project may be bid low in an effort to secure the project. This may seem like it saves money up front; however, it can increase cost and time down the line and increase project risk.
By bidding realistically, fair contract prices and accurate durations can be established from the beginning. These will aid in the establishment of a resolution of the claim and prevent unnecessary debate and analysis while increasing objectivity and accuracy.
With a clearly defined and documented construction approach and a well conceived plan, many claims can be avoided from unforeseen events and reduce the project risk.
Realistic Bid and Evaluation
Notes: Prebid questions? Unbalanced bids, engineers estimate, bid schedules (discuss in risk management?) - Briggs

## Slide 18: How can we do better?
Submit a claim when it is first discovered
Saves time, money, and effort
Improves partnerships and accuracy of the claim
Don’t let claims sit
Notes: Risk management fuel index.
Force account
Substantial increase of major items

## Slide 19: How can we do better?
P6 database, Ebuilder, DocExpress, Sitemanager, AASHTOWare Project, SmartPM.
Keep detailed records – record retention plan and management
Use proper record management – locked down to retain transparency and fact
Use document management for all correspondence, contract documents and schedules

## Slide 20: What is Next?
Risk Management
Documentation Controls
Resource Loading
Documentation: Ebuilder, DocExpress, Sitemanager
Schedule: Microsoft Project, P6, ASTA Power Project, Phoenix Project
Reporting: Power BI, SmartPM, Tableu
Risk Management: SmartPM, Claim Digger, InEight
Notes: (Cost load a schedule (P6) accountability and transparency) explain labor, equipment, material and cost

## Slide 21: Resolution!
Just the Facts!

## Slide 22: Claims Management – The Future
Finally…The End